## Sheet1
General principles
Public functions for 2d/3d should be same if arguments exactly the same but not otherwise (rather than using same function with dummary argument, even if that happens behind the scenes)
Public functions should be fully documented in header comments
Make sure all examples only use public functions
Put all non-essential functions into code\internal if not required for general use
Old function name | New function name | New function file exists | New function code written | New function help written | Tested | Test script (in /tests) | 2D/3D/Both | New function location | Action
fn_add_absorbing_layer | fn_2d_add_absorbing_layer.m | Yes | Yes | Yes | Yes | test_2d_meshing_functions | 2D | code
| fn_2d_add_crack.m | Yes | Yes | Yes | Yes | test_2d_defects | 2D | code | Needs checking (e.g. with fluid-solid interfaces but believed to work).
fn_add_scatterer | fn_2d_add_inclusion_or_void | Yes | Yes | Yes | Yes | test_2d_defects | 2D | code
fn_create_smooth_random_blob | fn_2d_create_smooth_random_blob.m | Yes | Yes | Yes | Yes | test_2d_defects | 2D | code
| fn_2d_random_walk | Yes | Yes | Yes | Yes | test_2d_defects | 2D | code
| fn_2d_structured_mesh_rectangular_els.m | Yes | Yes | Yes | Yes | test_2d_meshing_functions | 2D | code
fn_isometric_structured_mesh | fn_2d_structured_mesh_triangular_els.m | Yes | Yes | Yes | Yes | test_2d_meshing_functions | 2D | code
| fn_3d_add_absorbing_layer.m | [5 empty] | 3D | code | Needs facet surface description, then use internal function for getting distance to surface
| fn_3d_add_crack.m | Yes | Yes |  |  |  | 3D | code | Needs checking (e.g. with fluid-solid interfaces but believed to work).
| fn_3d_add_inclusion_or_void | [5 empty] | 3D | code | Generalise 2D one, based on facet surface description
| fn_3d_create_smooth_random_blob.m | [5 empty] | 3D | code | Generalise 2D version - some sort of spherical harmonics to get random surface or is tcode easier way?
| fn_3d_find_nodes_nearest_to_surface.m | [5 empty] | 3D | code | 3d version of find nodes on line in 2d. Should also return surface normals and handle multiple facets Rename both to 'nearest_to' rather than 'on'. Use fn_signed_dist_to_bdry
| fn_3d_structured_mesh_hexahedral_els.m | Yes | Partly |  |  |  | 3D | code | Should make it so that general 3d bdry can be specified rather than just a cuboid (to provide same functionality as 2d versions)
| fn_3d_tetrahedral_structured_mesh.m | No | No |  |  |  | 3D | code | They won't be regular tetrahedra! Should make it so that general 3d bdry can be specified rather than just a cuboid (to provide same functionality as 2d versions)
| fn_ABAQUS.m | Yes | No |  |  |  |  | code/internal/abaqus | Finish it! But in general, should be in code/internal functions.
fn_add_fluid_solid_interface_els.m | fn_add_fluid_solid_interface_els.m | Yes | Yes | Yes | Not for 3D | test_2d_meshing_functions | Both | code | Should work for 2d and 3d but latter needs checking
fn_BristolFE_v2.m | fn_BristolFE_v2.m | Yes | Yes | Yes |  | multiple places | Both | code/internal
fn_calc_element_centres.m | fn_calc_element_centres.m | Yes | Yes |  |  |  | Both | code/internal
fn_convert_disps_to_forces_v2.m | fn_convert_disps_to_forces_v2.m | Yes | Yes |  |  |  | Both | code/internal | Should work in 3D - needs checking
fn_display_result_v2.m | fn_display_result_v2.m | Yes | Yes |  |  |  | Both | code/internal | 3D probably needs some tweaking, but basically works
fn_dist_point_to_bdry_2D.m | fn_signed_dist_to_bdry | Yes | Yes |  | Yes |  | Both |  | Superceded by fn_signed_dist_to_bdry.m. Check for usage in code, but eventually delete
fn_elements_in_region.m | fn_2d_elements_in_region.m |  | Update |  |  |  |  | code | Check why 2 functions - poss one uses mod and the other uses nds and els. probably need new version for 2D and 3D that uses fn_signed_dist_to_bdry.m
fn_elements_in_region2.m |  |  | Obsolete |  |  |  |  | Remove
| fn_estimate_max_min_vels.m | Yes | Yes |  | Yes |  | Both | code
| fn_FE_entry_point.m | Yes | Yes |  | Yes |  | Both | code | Tidy up. Remove options to call obsolete versions
| fn_find_adjacent_els.m | [6 empty] | code/internal
| fn_find_free_edge_nds.m | [5 empty] | 2D | code/internal | Need generalising for 3D - used in subdomain stuff
| fn_find_free_edges.m | [5 empty] | 2D | code/internal | Need generalising for 3D - used in subdomain stuff
| fn_find_node_nearest_to_point.m |  | Done |  |  |  | Both | code | None
fn_find_nodes_on_line | fn_find_nodes_nearest_to_line.m |  | Generalise |  |  |  | 2D | code | Should handle multiple line segments and return surface normals at each node too. Not sure when needed, but this should be generalised in 3d too with same arguments - it doesn't need to be limited to 2d
| fn_find_surrounding_els.m | [6 empty] | code/internal
| fn_find_surrounding_nds.m | [6 empty] | code/internal
| fn_gaussian_pulse.m |  | Done |  |  |  | Both | code | None
| fn_get_edges.m | [7 empty] | Moved into fn_display_result
| fn_get_min_max_element_sizes.m |  | Done |  |  |  | Both | code | None
| fn_get_plot_vals_v3.m |  | Obsolete? | [5 empty] | Obs
| fn_get_plot_vals_v4.m | [7 empty] | Obs
| fn_get_suitable_el_size.m |  | Done |  |  |  | Both | code | None
| fn_get_suitable_time_step.m |  | Done |  |  |  | Both | code | None
| fn_gl_ind_for_nd_and_dof.m |  | Done |  |  |  |  | code/internal
| fn_isotropic_stiffness_matrix.m |  | Done |  |  |  | Both | code/internal | None
| fn_plot_3d_element.m | [7 empty] | Obs
| fn_plot_line.m | [6 empty] | code/internal
| fn_pogoFE.m |  | Done |  |  |  |  | code/internal/pogo | Need to try and get field output working
| fn_point_in_element.m | [7 empty] | Obs
| fn_prepare_animation.m |  | Generalise |  |  |  | 2D | code | Generalise to 3D as well - need to decide what 3D animation looks like!
| fn_read_pogo_global_matrix_values_from_files.m |  | Done |  |  |  |  | code/internal/pogo
| fn_remove_fluid_solid_interface_els.m |  | Generalise |  |  |  | 2D | code | Generalise to 3D as well
| fn_run_animation.m |  | Generalise |  |  |  | 2D | code | Generalise to 3D as well
| fn_show_geometry.m |  | Done |  |  |  | Both | code | Entry point for fn_display_result_v2, but just set to show model.
| fn_signed_dist_to_bdry.m |  | Done |  |  |  | Both | code
fn_set_els_inside_bdry_to_mat | No longer separate function.
| fn_matl_isotropic_solid_defined_by_velocities | Yes | Yes | Yes
| fn_matl_isotropic_solid_defined_by_stiffness | Yes | Yes | Yes
| fn_matl_fluid_defined_by_velocity | Yes | Yes | Yes
| fn_matl_fluid_defined_by_stiffness | Yes | Yes | Yes